DIGITAL TRANSFORMATION PROPOSAL Electronic Document Management System & Integrated School Management Portal

| Prepared For: Nigerian Navy College of Health Sciences, Offa Website: www.nnchsoffa.edu.ng | Date: February 2026 Document Type: Project Scope & Cost Proposal |
| --- | --- |

# 1. Executive Summary

This proposal outlines a comprehensive digital transformation programme for the Nigerian Navy College of Health Sciences (NNCHS), Offa. The project covers two integrated systems: an Electronic Document Management System (EDMS) for the digitization and secure management of institutional records, and a full-featured School Management Portal covering admissions, academic operations, examinations, certification, and alumni management, inclusive of a Training Centre module.

The existing website (nnchsoffa.edu.ng) is a lightweight static HTML site with no meaningful backend infrastructure. Our recommendation is to build a brand-new, modern web platform from scratch and retire the current site, migrating all relevant content into the new system. This approach is more cost-effective and scalable than retrofitting the old site.

The entire project will be executed across four phases over an estimated 18-month period, with a total investment range of ₦85,000,000 – ₦110,000,000 depending on final specifications and infrastructure preferences (cloud vs. on-premise).

# 2. Project Scope

## 2.1 Component A — Electronic Document Management System (EDMS)

The EDMS will digitize, organize, and secure all institutional records from 1986 to date. Key features include:

- Digitization of historical records: student files, results, staff records, minutes, memos, and academic reports (1986–2018). Records from 2019 onwards are already in soft copy and will be imported directly.

- Secure electronic document repository with role-based access control (RBAC) — different access levels for Commandant, academic staff, admin staff, and students.

- Workflow automation for approvals, memos, and interdepartmental communication.

- Searchable document indexing and tagging with advanced filter and full-text search capability.

- Comprehensive audit trails for all document access, modification, and deletion events.

- Integration with the School Management Portal and finance system.

- Human Resource Management (HRM) module for staff records, leave management, and payroll data.

Note: Physical document scanning and indexing from 1986–2018 will require a dedicated data entry/scanning team on the client's side, or can be quoted separately as a managed digitization service.

## 2.2 Component B — School Management Portal

The portal will cover both mainstream students and the Training Centre operations under one unified platform.

Admissions Management

- Online application submission with digital document upload

- Application fee payment integration (Paystack/Flutterwave)

- Screening and shortlisting workflow with admin dashboard

- Automated admission letter generation and email/SMS delivery

- Acceptance tracking and registration confirmation

Student Records Management

- Centralized student biodata and profile management

- Course registration and academic history archive

- Fee tracking and payment integration

- Student dashboard with access to personal academic records

Academic Operations

- Lecturer course allocation and teaching load management

- Online and Virtual Classes — live sessions with recording and replay capability; built-in Q&A chat and file sharing during sessions

- Automated timetable generation

- Attendance tracking (manual and QR-code based)

- Academic calendar management

Examination & Results Management

- Continuous Assessment (CA) input by lecturers

- Secure result submission with approval workflow

- Automated result computation and grading

- Online result publication (student portal)

- Transcript generation and download

Certification & Alumni Management

- Digital certificate generation with embedded security features

- QR code-based certificate verification portal (publicly accessible) to prevent forgery

- Alumni database with searchable directory

- Certificate reprint and verification request portal

Additional Recommended Features

- SMS and email notification engine for admissions, results, fees, and events

- Finance/bursary dashboard with payment receipts and fee defaulter tracking

- Mobile-responsive design (works on phones, tablets, desktops)

- Admin analytics dashboard — enrollment stats, result summaries, attendance reports

- Document e-signing capability for approvals

- Offline-capable Progressive Web App (PWA) version for low-connectivity environments

# 3. Website Strategy — New Build vs. Integration

The current NNCHS Offa website is a static HTML site with minimal functionality — no database, no user management, and no backend logic beyond a basic student/staff login link. Attempting to integrate new systems into this existing site would be technically restrictive and more expensive in the long run.

| Integration with Existing Site | New Build (Recommended) |
| --- | --- |
| Limited by existing HTML structure | Modern, scalable architecture from day one |
| Difficult to add complex features | Purpose-built for all required features |
| Higher technical debt over time | Clean codebase, easier to maintain |
| No existing backend to extend | Full backend with API from the start |
| Risk of breaking existing content | Seamless content migration from old site |

Recommendation: Build a brand-new platform. The existing website content (About, Departments, Events, Gallery) will be migrated to the new portal. The new site will retain the nnchsoffa.edu.ng domain.

# 4. Implementation Phases & Timeline

The project is structured into four phases to ensure a controlled, risk-managed delivery. Each phase ends with a review and sign-off before the next begins.

| Phase | Deliverables | Duration | Approx. Cost (₦) |
| --- | --- | --- | --- |
| Phase 1 — Foundation & EDMS | Infrastructure setup, EDMS (document repository, RBAC, audit trails, HR module), website skeleton | 3 Months | 20,000,000 – 26,000,000 |
| Phase 2 — School Portal Core | Admissions module, student records, fee payment integration, academic calendar, timetable | 4 Months | 22,000,000 – 28,000,000 |
| Phase 3 — Academic & Exams | Virtual classroom (with recording/replay), attendance, CA input, results, transcript, workflow approvals | 5 Months | 25,000,000 – 32,000,000 |
| Phase 4 — Certification, Alumni & Launch | Digital certificates with QR verification, alumni portal, notifications engine, UAT, training & go-live | 3 Months | 18,000,000 – 24,000,000 |
| TOTAL ESTIMATE |  | ~15 Months | ₦85,000,000 – ₦110,000,000 |

* Timeline and costs are estimates based on the scope described. Final figures will be confirmed after a detailed requirements workshop with the NNCHS team.

# 5. Cost Breakdown Summary

The following provides a transparent breakdown of cost categories across the full project.

| Cost Category | Estimated Range (₦) |
| --- | --- |
| Software Development (all modules) | ₦60,000,000 – ₦78,000,000 |
| UI/UX Design | ₦4,000,000 – ₦6,000,000 |
| Infrastructure (Cloud Hosting — 1st Year) | ₦5,000,000 – ₦8,000,000 |
| Data Migration & Content Setup | ₦3,000,000 – ₦5,000,000 |
| Integration (Payment, SMS, Email APIs) | ₦2,000,000 – ₦3,500,000 |
| Quality Assurance & Testing | ₦3,000,000 – ₦4,500,000 |
| Training & Documentation | ₦2,000,000 – ₦3,000,000 |
| Project Management | ₦3,000,000 – ₦4,000,000 |
| Contingency (5%) | ~₦4,100,000 – ₦5,500,000 |
| TOTAL | ₦85,000,000 – ₦110,000,000 |

Annual maintenance and support (post-launch) is recommended at 15–20% of total development cost, approximately ₦12,750,000 – ₦22,000,000 per year, covering hosting, updates, security patches, and helpdesk support.

Note on Physical Digitization: If a managed scanning and indexing service for historical records (1986–2018) is required, this will be scoped and costed separately based on the volume of physical documents.

# 6. Key Assumptions & Dependencies

- Client will provide timely access to relevant stakeholders for requirements gathering workshops.

- Physical document scanning (1986–2018) will either be handled by the client or quoted as a separate service.

- The College will procure or provide stable internet connectivity for cloud-hosted services.

- Payment gateway integration (Paystack/Flutterwave) will require the College to have a registered business account with the selected provider.

- Client will designate a project coordinator to liaise with the development team throughout.

- Third-party services (SMS, email, video streaming) will incur ongoing operational costs billed by the respective providers separately.

# 7. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Scope creep | Medium | Detailed change request process with costing for additions |
| Slow client approvals delaying phases | Medium | Defined SLA for feedback turnaround at each milestone |
| Poor internet connectivity at campus | Medium | Offline-capable PWA features; option for hybrid on-premise server |
| Data loss during migration | Low | Full backup before any migration; staged migration with rollback plan |
| Resistance to adoption from staff | Medium | Comprehensive training programme and user-friendly UI/UX design |

# 8. Recommended Next Steps

To proceed, we recommend the following:

- Proposal Review & Acceptance — Review this document and confirm intent to proceed.

- Discovery Workshop — A 1–2 day session with key NNCHS stakeholders to finalise requirements, confirm priorities, and agree on the technical stack.

- Contract & SLA Sign-off — Formal agreement covering scope, deliverables, payment milestones, and support terms.

- Kick-off — Phase 1 begins with infrastructure setup and project team onboarding.

Suggested payment structure: 30% upfront, 30% at Phase 2 delivery, 25% at Phase 3 delivery, 15% at final go-live.

We look forward to partnering with NNCHS Offa on this landmark digital transformation. For further information, please contact us to schedule a discussion.